## Slide 1: MPI Forum RCM/FRM Meeting Procedure

## Slide 2: At the “RCM” (Feb 22 – Feb 25) MPI Forum Chair
Present the compiled list of changes since the Release Candidate Document was published that have been made and will be made before completing MPI 4.0.
Already Done
(chap. cmte. changes at RCM)
Fix whitespace on p. 483
...
To Do
(errata at FRM)
Fixes for Big Counts
...
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 3: Immediately (By This Friday, Feb 26) Chapter Committee Chairs
Create issues in mpi-forum/mpi-issues repository for all remaining issues
  Add them to the MPI 4.0 project
If you already have an issue, you’re done!
Issues that are being tracked across multiple pull requests either need to combine the pull requests or separate the issues.
  There should be a 1:1 mapping from issue to pull request.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 4: Immediately MPI Standard Document Editor
Merge all pull requests that have been approved (at the December meeting and the February meeting) back into the mpi-4.x branch.
Create a new branch called mpi-4-rc-june starting at the point where the above work is completed.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 5: Between Now and April 26 Chapter Committee Chairs
Create new pull requests for all issues that were delayed and new issues raised during February meeting.
  New pull requests should be made against the new mpi-4-rc-june branch
  Focus on “emergency fixes” for newly introduced features. Long-term cleanup should aim for MPI 4.1.
If you have existing text in the mpi-4-rc branch, you can use `git cherry-pick` to replay your commits on a new branch based on mpi-4-rc-june (example on next slide).
Discuss changes in virtual meetings.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 6: Example of Replaying Existing Text
$ git remote –v mpi-forum https://github.com/mpi-forum/mpi-standard.git (fetch) mpi-forum https://github.com/mpi-forum/mpi-standard.git (push) wesbland https://github.com/wesbland/mpi-standard.git (fetch) wesbland https://github.com/wesbland/mpi-standard.git (push) $ git fetch –all $ git checkout –b intro_fixes mpi-forum/mpi-4-rc-june $ git cherry-pick cf514cc $ git cherry-pick a55a6d3 $ git cherry-pick 1eb2094 $ git cherry-pick f098644
$ # Continue making edits from here...
Find old Pull Request on GitHub and look at “Commits” tab

## Slide 7: Problems Finishing 4.0
It’s not clear when an issue is ready to be merged
  Some issues are either being merged too early (e.g., see February RC)
  Some are merged later than necessary (makes RC unstable at the end of the cycle)
There are too many issues that should be delayed for MPI 4.1 clogging up the 4.0 bandwidth
  Large, non-critical issues can delay MPI 4.0 further

## Slide 8: When Should an Issue be Merged?
We need a definitive way to say that an issue is ready to be merged into the RC.
In the normal process, votes determine this. Things are clear. 👍
When merging before the votes (RC model), things aren’t clear and merged too early. 👎
Suggestion: We have a “release manager” who ensures that PR have adequate reviews and that all items are addressed before marking them as ready to go for Bill.
  Further suggestion: Wes is the release manager.

## Slide 9: We’re Seeing Too Many New Changes
Original goal:
Fix problems with MPI 4.0 that were introduced by MPI 4.0
  Partitioned Communication, Sessions, MPI_T Events, etc.
Fix other emergency issues that would cause backward incompatibilities
Reality:
Many issues that are unrelated to these goals are being raised for 4.0 and are likely to delay things again.
  Example: progress definitions, “MPI process”, etc.
  31 issues currently tagged with “mpi-4.0”

## Slide 10: Suggestion: Release Manager as Gatekeeper
Most items currently being considered for MPI 4.0 are being considered “because we have time”.
  We don’t have time and many of these little things are piling up and could delay MPI 4.0 again.
Wes will be going through the project board and relabeling things that do not cause breaking changes for MPI 4.0 and moving them to MPI 4.1.
  Anything already merged since the Feb meeting (and not reverted) will be kept in.
These issues can (and should) still be addressed, but we’ll work on them immediately after the June meeting through the normal process.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 11: Proposed Resolutions
Issues to continue for MPI 4.0 (12):
  #424, #433, #437, #438, #440, #444, #454, #456, #459, #460, #489, #491
Issues to move to MPI 4.1 (8):
  #350, #443, #449, #457, #466, #468,#492, #493
Issues already merged (pending vote) for MPI 4.0 (9):
  #435, #453, #458, #461, #462, #463, #464, #465, #488
Issues to close (2):
  #405, #450

## Slide 12: 6 weeks before the FRM (April 26) Chapter Committee Chairs
Resolve all remaining open issues from the previous lists
  Work with Bill to merge any changes (prior to errata vote at the FRM)
Complete all informal readings for any opened PRs
All PRs need to be posted by April 26 to give time for Bill to review and merge them.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 13: 4 weeks before the FRM (May 10) MPI Standard Document Editor
Publish a new Release Candidate Document
  Anything that was officially voted in at the previous meeting goes into the mpi-4.x branch.
  Anything that still needs a vote goes into the mpi-4-rc-june branch.
  The mpi-4-rc-june branch should be based on (or merged with) the mpi-4.x branch.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 14: 2 weeks before the FRM (May 24) MPI Forum Chair
MPI Forum officer nominations close
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 15: At the FRM (June 7 – June 9) Chapter Committee Chairs
Present changes since the December 2020 RCM

## Slide 16: At the FRM (June 7 – June 9) MPI Forum Secretary
Conduct a ballot for each change that happened between the RCM and FRM that was on the previously published list.
  This follows “errata” rules and anything that fails will need to be reverted.
Conduct a ballot for each change that happened between the RCM and FRM that was not on the previously published list.
  This follows the “no-no” rules and anything that fails will need to be reverted.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 17: At the FRM (June 7 – June 9) MPI Forum Chair
Compile a list of all still-unresolved issues that could be fixed before releasing MPI 4.0.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 18: At the FRM (June 7 – June 9) MPI Forum Secretary
If there is anything left on the chair’s list, on a different date than the previous ballots, hold another ballot about whether to delay ratification.
  If this passes, repeat the FRM at the next meeting.
Conduct a ballot on whether to ratify the entire document
  If this passes, Bill publishes the final version of MPI 4.0 to the MPI Forum website.
  If this fails, start back at the beginning of this slide deck.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021

## Slide 19: At the FRM (June 7 – June 9) MPI Forum Secretary
Conduct ballots for the MPI Forum Officers
  Following the procedures in the procedures document (i.e., continue ballots until some candidate for each office has a majority of non-abstain votes).
New officers begin their term and work with the old officers to transfer knowledge, state secrets, executive washroom keys, etc.
FRM
RCM
March 2021
April 2021
February 2021
May 2021
June 2021